## Planilha1
		Trialist personal data management
1		signup: create account	3	12		134	períodos
2		login	1	4		67	dias de	2	períodos
3		trialist dashboard (lists: subissions, pending issues)	5	20		16,75	semanas de	4	dias
4		change password	1	4		4,19	meses
5		reset password	2	8
6		set preferred language	1	4
		Trialist trial record submission		0
7		list own clinical trial submissions	1	4
8		start submission and determine mandatory registration languages	3	12
9		submission status overview	3	12
10		edit clinical trial record in each language	8	32
11		upload submission attachments	3	12
12		view and handle pending issues	8	32
13		request support	2	8
14		upload trial record in ICTRP XML format	5	20
		Reviewer trial record revision		0
15	login		1	4
16		reviewer dashboard (list: assigned submissions, pending issues)	3	12
17		sumbission management reports	8	32
18		review submission and post issues at field and record level	8	32
19		review submission attachments	3	12
20		manage out-of-band verification	3	12
21		approve translation	3	12
22	view history		8	32
	basic search		8	32
		advanced search	8	32
		Citizen public interface		0
23	basic search		1	4
24		advanced search	1	4
25		download selected records	5	20
26		view record history	3	12
27		view attached files	2	8
28	set preferred language		1	4
29	FAQ		3	12
30	contact form		1	4
		Administrator operations management		0
31		edit field-level help	3	12
32		edit FAQ	2	8
33		edit controlled vocabularies	1	4
34		edit UI translation	3	12
35		manage reviewers	1	4
36		view reports	8	32
37				0
38				0
39		Review automated tests		0
40		automated testing scripts	2	8
41		creation and maintenance of test fixtures	2	8
42		manual test plan		0
43		Documentation review	8	32
44		specification wiki editing		0
45		ticket creation, review and updates		0
46		deployment how-to		0
47		operating manual		0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0